## Risk Register (Company)
[6 empty] | Risk Assessment |  |  |  | Plan
Code | Date Created | Description | Category | Type | Owner | Likelihood | Impact | Risk Response | Trigger | Mitigation / Enhancement | Contingency | Progress | Status | Date Updated
1 | 2023-02-26 | Two team members were missing in this development stage (Sprint 1). There is a risk that these team members lack suficient knowledge to catch up with the rest of the team, and therefore not contribute to their full pontential (creating further problems) | Team | Negative |  | Low | High | Avoid | Future tasks assigned to missing members being left behind / missing team member performance lacking behind others | We propose to communicate with these team members and understand the number of active developers we will have in the team in future sprints so we can readjust the expected amount of work assigned to each developer. | Redelegate work throughout the other team members | Team members already up to speed. Having missed the 1st sprint doesnt seem to be impacting re-integration | Resolved | 2023-03-23
2 | 2023-02-26 | We could create products that are not innovative and don’t bring much value to the market. | Scope | Negative |  | Medium | Low | Mitigate | Final product does not gain traction and better alternative with similar / identical features is already implemented, making our product unable to capture users. | To combat this we focused on exploring the competition and putting effort into understanding exactly what the client wants and what are our ideas to implement it. | Expand on the product and implement new features, in order to stand our from existing alternatives |  | Open | 2023-03-23
3 | 2023-02-26 | We have never worked together before therefore there are difficulties in understanding how to work as a team and guarantee that the project gets done and runs smoothly. | Team | Positive |  | High | Medium | Exploit | General team concensus that team members are significantly more apt to work in a collaborative environment, and are consequently better at developing quality products and adapting to new peers. | We learned that it’s necessary to plan task division and provide clear instructions on what everybody should be doing. Forcing the team to work unanimously and in a cooperative way will allow us to grow and develop good products | Explore new ways in which the team could increase productivity, and attempt to identify what is stopping us from improving as a group | Good progress, majority of team elements learning cooperation skills | Open | 2023-03-23
Note on F2: ====== ID#AAAAstjji9w tc={0FA4324B-C31E-244F-B363-4BB620401240} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Team member responsible for managing this risk
Note on J2: ====== ID#AAAAstjji9E tc={B8D4D8B6-CA98-8A4C-8B84-A50C3759C577} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Triggers, symptoms, and warning signs of risks’ occurrence
Note on K2: ====== ID#AAAAstjji9Y tc={4C137199-794F-BC40-9523-A240A1DB0C11} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: actions to reduce (increase) the probability and/or impact of an adverse risk (opportunity) event to be within acceptable threshold limits
Note on L2: ====== ID#AAAAstjji9A tc={999A5471-1EE7-3C40-A1F4-D192A1DF25DC} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Plan devised for an exceptional risk that, though unlikely, would have catastrophic consequences
Note on M2: ====== ID#AAAAstjji80 tc={DF0334D3-E06A-5B48-BAD2-0AAB6870012D} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Status of the actions

## Risk Register (Team A)
[6 empty] | Risk Assessment |  |  |  | Plan
Code | Date Created | Description | Category | Type | Owner | Likelihood | Impact | Risk Response | Trigger | Mitigation / Enhancement | Contingency | Progress | Status | Date Updated
Note on F2: ====== ID#AAAAstjji8c tc={07333433-DD80-B644-B49C-798BFB6FA946} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Team member responsible for managing this risk
Note on J2: ====== ID#AAAAstjji9I tc={7FEB86AF-1EE9-DD4F-8ABA-9CDFCF63455B} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Triggers, symptoms, and warning signs of risks’ occurrence
Note on K2: ====== ID#AAAAstjji9U tc={F4833E0F-EFA6-5549-B993-B8D540354A75} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: actions to reduce (increase) the probability and/or impact of an adverse risk (opportunity) event to be within acceptable threshold limits
Note on L2: ====== ID#AAAAstjji9g tc={440A2A7D-EE1D-BA46-9967-CEDA579ACEA7} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Plan devised for an exceptional risk that, though unlikely, would have catastrophic consequences
Note on M2: ====== ID#AAAAstjji9o tc={A6BA6BC6-B656-DA4A-ADF5-0BFB83648A9F} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Status of the actions

## Risk Register (Team B)
[6 empty] | Risk Assessment |  |  |  | Plan
Code | Date Created | Description | Category | Type | Owner | Likelihood | Impact | Risk Response | Trigger | Mitigation / Enhancement | Contingency | Progress | Status | Date Updated
Note on F2: ====== ID#AAAAstjji9M tc={0E51C588-2585-4F45-997C-9FA2A682C135} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Team member responsible for managing this risk
Note on J2: ====== ID#AAAAstjji8w tc={626D2185-FEFA-604A-988A-A78ECC50F3F9} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Triggers, symptoms, and warning signs of risks’ occurrence
Note on K2: ====== ID#AAAAstjji8k tc={AB39BBC6-A1A0-CF42-ABE8-AED78B0F0F4D} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: actions to reduce (increase) the probability and/or impact of an adverse risk (opportunity) event to be within acceptable threshold limits
Note on L2: ====== ID#AAAAstjji9Q tc={F4A464FE-0273-914E-B839-B8282EB02C3A} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Plan devised for an exceptional risk that, though unlikely, would have catastrophic consequences
Note on M2: ====== ID#AAAAstjji84 tc={A44C2E91-9140-B546-8CAF-8BBE7490B4FA} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Status of the actions

## Risk Register (Team C)
[6 empty] | Risk Assessment |  |  |  | Plan
Code | Date Created | Description | Category | Type | Owner | Likelihood | Impact | Risk Response | Trigger | Mitigation / Enhancement | Contingency | Progress | Status | Date Updated
Note on F2: ====== ID#AAAAstjji8o tc={C3DA142D-67C9-664B-827D-289EEE9D2C5F} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Team member responsible for managing this risk
Note on J2: ====== ID#AAAAstjji90 tc={6529AA15-3BBF-4F4A-A3AF-9212212534AB} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Triggers, symptoms, and warning signs of risks’ occurrence
Note on K2: ====== ID#AAAAstjji9s tc={4253A76B-0A8B-A343-BB67-495FB9D9474D} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: actions to reduce (increase) the probability and/or impact of an adverse risk (opportunity) event to be within acceptable threshold limits
Note on L2: ====== ID#AAAAstjji94 tc={13497EC7-D581-D041-9337-E383E3D0C99C} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Plan devised for an exceptional risk that, though unlikely, would have catastrophic consequences
Note on M2: ====== ID#AAAAstjji9k tc={7792F358-BA4E-5B40-84A7-A20AC5139C3B} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Status of the actions

## Risk Register (Team D)
[6 empty] | Risk Assessment |  |  |  | Plan
Code | Date Created | Description | Category | Type | Owner | Likelihood | Impact | Risk Response | Trigger | Mitigation / Enhancement | Contingency | Progress | Status | Date Updated
Note on F2: ====== ID#AAAAstjji9c tc={CDF479FC-C36A-8D46-AA0D-BBC7C50F0C5C} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Team member responsible for managing this risk
Note on J2: ====== ID#AAAAstjji8s tc={995910E5-E9E1-DA4F-820D-D3D591AAD7BA} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Triggers, symptoms, and warning signs of risks’ occurrence
Note on K2: ====== ID#AAAAstjji98 tc={34D24A87-F791-EA4A-8323-293D7191F837} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: actions to reduce (increase) the probability and/or impact of an adverse risk (opportunity) event to be within acceptable threshold limits
Note on L2: ====== ID#AAAAstjji88 tc={8CA5F172-B430-D849-ABF2-126EEBC760EE} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Plan devised for an exceptional risk that, though unlikely, would have catastrophic consequences
Note on M2: ====== ID#AAAAstjji8g tc={6D27B9E7-EC10-1C4A-B267-C2A52AC0B98B} (2023-03-25 00:13:06) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Status of the actions

## Risk Matrix
impact
likelihood |  | Very Low | Low | Medium | High | Very High
| Very High | Yellow | Orange | Red | Dark Red | Dark Red
| High | Yellow | Yellow | Orange | Red | Dark Red
| Medium | Green | Yellow | Yellow | Orange | Red
| Low | Green | Green | Yellow | Yellow | Orange
| Very Low | Green | Green | Green | Yellow | Yellow

## data
Risk
Category |  | Type |  | Level | Response |  | Status
Team | Problems with availability of team members, internal communication, ability to work as a team, lack of skills, leadership, etc. | Positive | Opportunity | Very Low | Avoid | Avoid should be used when you want to be sure that the negative risk is not encountered | Identified
Customer | Availability, ease of communication, responsiveness and maturity of customer and other stakeholders. | Negative | Risk | Low | Mitigate | Try to ensure it doesn’t happen | Open
Scope | Complexity, uncertainity, volatility or ignorance of scope, requirements, functionality, application domain or target users. |  |  | Medium | Transfer | Give to someone else like insurance company | Resolved
Dependencies | Dependency of external resources such as APIs, data sets, devices, documentation, etc., wich might not be available or not have the needed quality. |  |  | High | Accept | Accept the risk when you can or you have to
Management | Problems with project estimation, planing, monitoring and control, such as unreliable estimates, difficulty to track progress, difficulty to control changes, etc. |  |  | Very High | Exploit | Use this strategy when you REALLY want the positive risk to happen
Technical | Technical complexity, lack of experience with technologies, imature technologies, uncertainity regarding technical solution. |  |  |  | Enhance | Try to ensure that the positive risk occurs
Other |  |  |  |  | Share | Get a third party involved to try to help you best capture the positive risk
[5 empty] | Accept | Enjoy the benefits of the opportunity